## Project Plan
Phase | Phase Name | Task # | Task | Subtask | Days
0 | Project Setup | 0.1 | Create project structure | Create monorepo folders: /backend-springboot, /backend-fastapi, /frontend, /data, /chroma_db | 0.5
|  | 0.2 | FastAPI environment setup | Create virtual environment, requirements.txt, .env file with OpenAI API key
|  | 0.3 | Spring Boot project setup | Generate project via Spring Initializr — Web, JPA, H2, Lombok, Validation
|  | 0.4 | Database initialisation | Initialise H2 in-memory DB for Spring Boot; SQLite for FastAPI
|  | 0.5 | ChromaDB initialisation | Create local ChromaDB collection for knowledge base
1 | Spring Boot Foundation | 1.1 | Entity models | Create Student entity (name, email, phone, DOB) | 1.5
|  | 1.1 | Entity models | Create Application entity (student, status, submission date, decision)
|  | 1.1 | Entity models | Create DocumentRecord entity (application, type, file path, upload date)
|  | 1.2 | JPA Repositories | Create StudentRepository extending JpaRepository
|  | 1.2 | JPA Repositories | Create ApplicationRepository with custom queries
|  | 1.2 | JPA Repositories | Create DocumentRecordRepository
|  | 1.3 | Application controller | POST /api/applications — create new application
|  | 1.3 | Application controller | GET /api/applications/{id} — get application by ID
|  | 1.3 | Application controller | GET /api/applications — list all applications with filters
|  | 1.3 | Application controller | PUT /api/applications/{id}/status — update application status
|  | 1.4 | Student controller | POST /api/students — register student
|  | 1.4 | Student controller | GET /api/students/{id} — get student profile
|  | 1.5 | DTOs and mappers | Create request/response DTOs for Student, Application, DocumentRecord
|  | 1.5 | DTOs and mappers | Create mapper classes (Entity ↔ DTO)
|  | 1.6 | Global exception handler | Handle 404 Not Found, 400 Bad Request, 500 Internal Server Error
|  | 1.7 | H2 console setup | Enable H2 console at /h2-console for local dev debugging
2 | FastAPI Foundation | 2.1 | FastAPI app setup | Initialise FastAPI app, configure CORS, add middleware | 0.5
|  | 2.2 | SQLAlchemy models | Create Document model (id, application_id, type, file_path, status)
|  | 2.2 | SQLAlchemy models | Create ExtractionResult model (document_id, extracted_json, confidence)
|  | 2.2 | SQLAlchemy models | Create ValidationResult model (application_id, checks_json, score, decision)
|  | 2.3 | Pydantic schemas | Create schemas for Document upload, ExtractionResult, ValidationResult
|  | 2.4 | Document upload endpoint | POST /documents/upload — accept file, validate MIME (PDF/JPG/PNG), save to local disk
|  | 2.5 | Health check endpoint | GET /health — return service status and version
3 | Document Extraction | 3.1 | GPT-4o Vision base service | Convert image/PDF page to base64 | 1.0
|  | 3.1 | GPT-4o Vision base service | Build OpenAI Vision API call with structured JSON output
|  | 3.1 | GPT-4o Vision base service | Handle API errors, retries, and timeouts
|  | 3.2 | 10th Marksheet extractor | Design extraction prompt for 10th marksheet
|  | 3.2 | 10th Marksheet extractor | Extract: name, DOB, school, board, exam year, subjects, marks, percentage, pass/fail
|  | 3.2 | 10th Marksheet extractor | Return confidence score per field
|  | 3.3 | 12th Marksheet extractor | Design extraction prompt for 12th marksheet
|  | 3.3 | 12th Marksheet extractor | Extract: name, DOB, school, board, stream, exam year, subjects, marks, percentage
|  | 3.3 | 12th Marksheet extractor | Return confidence score per field
|  | 3.4 | Aadhar Card extractor | Design extraction prompt for Aadhar card
|  | 3.4 | Aadhar Card extractor | Extract: full name, DOB, gender, masked Aadhar number, address
|  | 3.4 | Aadhar Card extractor | Return confidence score per field
|  | 3.5 | PDF handler | Extract first 2 pages from PDF; convert to images for Vision API
|  | 3.6 | Extraction result storage | Save extracted JSON and confidence scores to SQLite
|  | 3.6 | Extraction result storage | Link extraction result to document record
4 | Validation Engine | 4.1 | Individual document validation | Check all required fields are present and non-empty | 1.0
|  | 4.1 | Individual document validation | Flag fields with confidence score below 70%
|  | 4.1 | Individual document validation | Check document type matches uploaded category
|  | 4.2 | Cross-document name matching | Compare student name across 10th, 12th, and Aadhar
|  | 4.2 | Cross-document name matching | Fuzzy matching with 80% similarity threshold
|  | 4.2 | Cross-document name matching | Flag mismatch with extracted values shown side by side
|  | 4.3 | Cross-document DOB matching | Compare DOB across all 3 documents — exact match required
|  | 4.3 | Cross-document DOB matching | Flag any mismatch with extracted values shown side by side
|  | 4.4 | Marks/percentage validation | Validate 10th percentage meets minimum eligibility (configurable threshold)
|  | 4.4 | Marks/percentage validation | Validate 12th percentage meets minimum eligibility (configurable threshold)
|  | 4.4 | Marks/percentage validation | Validate marks per subject are within valid range (0–100)
|  | 4.5 | Confidence scoring | Calculate per-document confidence score (average of field-level scores)
|  | 4.5 | Confidence scoring | Calculate overall application confidence score (weighted average)
|  | 4.6 | Decision engine | Auto-Approve: all checks pass + confidence ≥ 85%
|  | 4.6 | Decision engine | Auto-Reject: critical checks fail (DOB mismatch, marks below eligibility)
|  | 4.6 | Decision engine | Manual Review: checks pass but confidence between 60–85%
5 | RAG Knowledge Base | 5.1 | Knowledge base content | Write eligibility rules document (min marks, stream requirements per course) | 1.0
|  | 5.1 | Knowledge base content | Write board formats document (CBSE, ICSE, State board certificate formats)
|  | 5.1 | Knowledge base content | Write common FAQs document (document requirements, accepted formats)
|  | 5.2 | Embedding and ingestion pipeline | Chunk knowledge base documents into sections
|  | 5.2 | Embedding and ingestion pipeline | Generate embeddings using text-embedding-3-small
|  | 5.2 | Embedding and ingestion pipeline | Store embeddings in ChromaDB local collection
|  | 5.3 | RAG query service | Accept eligibility query (course applied, 12th marks, stream)
|  | 5.3 | RAG query service | Retrieve top-k relevant policy chunks from ChromaDB
|  | 5.3 | RAG query service | Pass context + query to GPT-4o for eligibility decision
|  | 5.4 | Eligibility check integration | Call RAG service after extraction and validation
|  | 5.4 | Eligibility check integration | Include RAG eligibility result in final verification report
6 | Workflow + Integration | 6.1 | FastAPI end-to-end pipeline | Chain: Upload → Extract → Validate → RAG check → Decision | 1.0
|  | 6.1 | FastAPI end-to-end pipeline | Run pipeline as background task (FastAPI BackgroundTasks)
|  | 6.1 | FastAPI end-to-end pipeline | Update document and application status at each pipeline step
|  | 6.2 | FastAPI verify endpoints | POST /verify/{application_id} — trigger full verification pipeline
|  | 6.2 | FastAPI verify endpoints | GET /verify/{application_id}/status — get current verification status
|  | 6.2 | FastAPI verify endpoints | GET /verify/{application_id}/report — get full verification report JSON
|  | 6.3 | Spring Boot HTTP client | Configure RestTemplate/WebClient to call FastAPI
|  | 6.3 | Spring Boot HTTP client | POST to FastAPI /verify/{application_id} on document submission
|  | 6.3 | Spring Boot HTTP client | GET from FastAPI /verify/{application_id}/report for results
|  | 6.4 | Spring Boot status update | Update Application status in DB based on FastAPI verification result
|  | 6.4 | Spring Boot status update | Expose GET /api/applications/{id}/report to return verification report to UI
|  | 6.5 | Re-verification support | Allow re-upload of a specific document
|  | 6.5 | Re-verification support | Trigger re-run of verification pipeline for updated document
7 | Streamlit UI | 7.1 | App shell and navigation | Initialise Streamlit app with sidebar navigation | 1.5
|  | 7.1 | App shell and navigation | Pages: New Application, Applications List, Application Detail
|  | 7.2 | New Application screen | Student registration form (name, email, phone, DOB, course applied)
|  | 7.2 | New Application screen | Document upload widgets: separate uploader for 10th, 12th, Aadhar
|  | 7.2 | New Application screen | Submit button — calls Spring Boot to create application and trigger verification
|  | 7.3 | Processing screen | Show per-document status: Pending / Extracting / Validating / Done / Failed
|  | 7.3 | Processing screen | Auto-refresh every 3 seconds until all documents processed
|  | 7.3 | Processing screen | Progress bar showing overall completion percentage
|  | 7.4 | Results — Extraction | Show extracted fields in structured table per document
|  | 7.4 | Results — Extraction | Highlight low-confidence fields in yellow
|  | 7.4 | Results — Extraction | Show confidence score per document
|  | 7.5 | Results — Validation | Show each validation check with Pass / Fail / Warning badge
|  | 7.5 | Results — Validation | Show reason for each failed or warning check
|  | 7.5 | Results — Validation | Side-by-side comparison for name/DOB cross-document checks
|  | 7.6 | Results — Decision | Show overall verdict: Approved / Rejected / Manual Review
|  | 7.6 | Results — Decision | Show overall confidence score and summary of checks
|  | 7.7 | Applications List screen | Table: ID, student name, status, submission date, decision
|  | 7.7 | Applications List screen | Filter by status; click row to open application detail
8 | Testing & Stabilisation | 8.1 | End-to-end testing | Full flow: UI → Spring Boot → FastAPI → GPT-4o → result in UI | 1.0
|  | 8.2 | Edge case testing | Low-quality/blurry document image
|  | 8.2 | Edge case testing | Name mismatch across documents
|  | 8.2 | Edge case testing | Missing required fields in document
|  | 8.2 | Edge case testing | Marks below eligibility threshold
|  | 8.2 | Edge case testing | Unsupported file format upload
|  | 8.3 | Bug fixes | Extraction accuracy issues — prompt tuning
|  | 8.3 | Bug fixes | Spring Boot ↔ FastAPI integration issues
|  | 8.3 | Bug fixes | UI rendering issues
|  | 8.4 | Documentation | README: prerequisites, setup steps, how to run both services
|  | 8.4 | Documentation | Document .env variables for both services
|  | 8.4 | Documentation | Document all API endpoints for Spring Boot and FastAPI

## Timeline
Day | Phases | Work Items | Cumulative Days
Day 1 | Phase 0 + Phase 1 | Project setup, Spring Boot entities, repositories, controllers | 1
Day 2 | Phase 1 + Phase 2 | Spring Boot DTOs, exception handler + FastAPI setup, models, upload endpoint | 2
Day 3 | Phase 3 | GPT-4o Vision base service, 10th & 12th marksheet extractor, Aadhar extractor | 3
Day 4 | Phase 4 | Individual validation, cross-doc name/DOB match, marks validation, decision engine | 4
Day 5 | Phase 5 | Knowledge base content, embedding ingestion, RAG query service, eligibility integration | 5
Day 6 | Phase 6 | FastAPI end-to-end pipeline, verify endpoints, Spring Boot HTTP client, status update | 6
Day 7 | Phase 7 | Streamlit: app shell, New Application screen, Processing screen | 7
Day 8 | Phase 7 + Phase 8 | Streamlit: Results screens, Applications List + End-to-end testing, edge cases | 8
Day 9 | Phase 8 | Bug fixes, prompt tuning, documentation, buffer | 9

## Effort Summary
Phase | Phase Name | Days (with AI) | Days (without AI)
0 | Project Setup | 0.5 | 1.0
1 | Spring Boot Foundation | 1.5 | 3.0
2 | FastAPI Foundation | 0.5 | 1.0
3 | Document Extraction Service | 1.0 | 3.0
4 | Validation Engine | 1.0 | 2.0
5 | RAG Knowledge Base | 1.0 | 2.0
6 | Verification Workflow + Integration | 1.0 | 2.0
7 | Streamlit UI | 1.5 | 3.0
8 | Testing and Stabilisation | 1.0 | 1.0
| TOTAL | 9.0 | 18.0

## Risk Register
# | Risk | Likelihood | Impact | Mitigation
1 | GPT-4o Vision accuracy on low-quality scans | Medium | High | Prompt tuning + confidence threshold flagging for manual review
2 | PDF multi-page complexity | Low | Medium | Limit processing to first 2 pages in v1
3 | Name spelling variations across documents | Medium | Medium | Fuzzy matching with configurable 80% threshold
4 | OpenAI API cost during testing | Low | Low | Use compressed images; cache extraction results in SQLite
5 | Spring Boot ↔ FastAPI integration errors | Medium | High | Validate API contracts with sample payloads before full integration
6 | ChromaDB accuracy for eligibility RAG | Low | Medium | Curate and test knowledge base content before ingestion